## Sheet1
| Project Name | Completion | Project Budget | Measure S Allocation | Other Funding | Measure S Expenditures as of 6/30/08 | Measure S Expenditures as of 3/31/08 | Measure S Expenditures Last Period
1 | Athletic Fields Phase I, Corsair Field | September 2008 | 4010000 | 4010000 | 0 | 487237 | 293879 | 193358
1A | Athletic Fields Phase I, John Adams | September 2008 | 4429445 | 4429445 | 0 | 129169 | 106289 | 22880
2 | Performing Arts Complex | June 2008 | 40479224 | 37486648 | 2992576 | 35909093 | 34927111 | 981982
3 | Career Opportunity Center | Future Project | 0 | 0 | 0 | 0 | 0 | 0
4 | Replacement Health, Fitness, PE | Future Project | 37525 | 37525 | 0 | 37525 | 37525 | 0
5 | Early Childhood Development/Childcare | In Planning | 11318000 | 7000000 | 4318000 | 3975 | 0 | 3975
6 | Malibu Site Acquisition and Facility | Not Scheduled | 26000000 | 25000000 | 1000000 | 2698528 | 2697255 | 1273
7 | Energy Efficiency Projects | In Planning | 25000 | 25000 | 0 | 10500 | 10500 | 0
8 | Satellite Campus Parking Facilities and Roadway Improvements | August 2009 | 5411382 | 5411382 | 0 | 680229 | 498814 | 181415
9 | Student Services Building | April 2012 | 94027100 | 59000000 | 0 | 1155545 | 0 | 1155545
10 | Pico Promenade Improvements | December 2008 | 1100000 | 1100000 | 0 | 61510 | 0 | 61510
| Project Totals |  | 151810576 | 143500000 | 8310576 | 41173311 | 38571373 | 2601938