## Sheet1
| Project Name | Completion | Project Budget | Measure U Allocation | Other Funding | Measure U Expenditures as of 6/30/08 | Measure U Expenditures as of 3/31/08 | Measure U Expenditures Last Period
A | Purchase of BAE Airport Site | Completed | 33000000 | 33000000 | 0 | 33000000 | 33000000 | 0
B | Emeritus College Facility | Completed | 9603782 | 8909940 | 693842 | 8909940 | 8909940 | 0
C | Purchase of 1738 Pearl Street | Completed | 749208 | 749208 | 0 | 749208 | 749208 | 0
D | PE Temp. Bldg. Replacement | Completed | 2797033 | 2797033 | 0 | 2797033 | 2797033 | 0
E | Remodel Library Village for Math | Completed | 1458690 | 1458690 | 0 | 1458690 | 1458690 | 0
F | SM Airport Campus Site Improvements | Completed | 4170264 | 4170264 | 0 | 4170264 | 4170264 | 0
G | SM Airport Campus West Building | Completed | 19709741 | 19709741 | 0 | 19709741 | 19709741 | 0
H | Theater Arts Renovation | Completed | 19492296 | 19576422 | 0 | 19487988 | 19487988 | 0
I | Earthquake Rpl. Liberal Arts North | Completed | 13473652 | 6352752 | 7120900 | 8749132 | 8744507 | 4625
J | Music Complex | Completed | 4552688 | 1934575 | 2618113 | 1957086 | 1900048 | 57038
K | Earthquake Rpl. Liberal Arts South | Completed | 16891384 | 6266314 | 10625070 | 5792649 | 6118771 | -326122
L | Shuttle Replacement Parking | Completed | 19010000 | 19010000 | 0 | 18967156 | 18927084 | 40072
M | North Quad Plaza | October 2008 | 11493568 | 11493568 | 0 | 6077333 | 3103733 | 2973600
N | Letters & Sci Demo/Restore | Future Project | 0 | 0 | 0 | 0 | 0 | 0
O | Student Services Building | April 2012 | 94027100 | 14246310 | 17256000 | 870894 | 846389 | 24505
P | Science Complex Addition | Future Project | 308000 | 308000 | 0 | 308336 | 308336 | 0
Q | Infrastructure & Safety | 2008 | 6859518 | 8007775 | 0 | 2324565 | 2319580 | 4985
R | Restroom Improvements | 2008 | 85000 | 85000 | 0 | 17501 | 17501 | 0
S | Master Planning | 2008 | 1605166 | 1605166 | 0 | 1461207 | 1433160 | 28047
T | 14th and Pico Project | On Hold | 319242 | 319242 | 0 | 319242 | 319242 | 0
| Project Totals |  | 259606332 | 160000000 | 38313925 | 137127965 | 134321215 | 2806750