## Sheet1
| Project Name | Completion | Project Budget | Measure S Allocation | Other Funding | Measure S Expenditures as of 9/30/08 | Measure S Expenditures as of 6/30/08 | Measure S Expenditures Last Period
1 | Athletic Fields Phase I, Corsair Field | September 2008 | 4010000 | 3942470 | 67530 | 2453372 | 855404 | 1597968
1A | Athletic Fields Phase I, John Adams | October 2008 | 4429445 | 4429445 | 0 | 1158558 | 145530 | 1013028
2 | Performing Arts Complex | Completed | 39479224 | 36486648 | 2992576 | 34784872 | 34547083 | 237789
3 | Career Opportunity Center | Future Project | 0 | 0 | 0 | 0 | 0 | 0
4 | Replacement Health, Fitness, PE | Future Project | 37525 | 37525 | 0 | 37525 | 37525 | 0
5 | Early Childhood Development/Childcare | In Planning | 11318000 | 7000000 | 4318000 | 9200 | 9200 | 0
6 | Malibu Site Acquisition and Facility | Not Scheduled | 26000000 | 25000000 | 1000000 | 5204392 | 2700488 | 2503904
7 | Energy Efficiency Projects | December 2009 | 667530 | 667530 | 0 | 10814 | 10500 | 314
8 | Satellite Campus Parking Facilities and Roadway Improvements | August 2009 | 5411382 | 5411382 | 0 | 1317844 | 977949 | 339895
9 | Student Services Building | April 2012 | 94027100 | 59425000 | 34602100 | 2266766 | 2266766 | 0
10 | Pico Promenade Improvements | December 2008 | 1100000 | 1100000 | 0 | 91543 | 72066 | 19477
| Project Totals |  | 186480206 | 143500000 | 42980206 | 47334886 | 41622511 | 5712375