## Sheet1
| Project Name | Completion | Project Budget | Measure U Allocation | Other Funding | Measure U Expenditures as of 9/30/05
A | Purchase of BAE Airport Site | Completed | 33000000 | 33000000 | 0 | 33000000
B | Emeritus College Facility | Completed | 9577223 | 8906048 | 693842 | 8909940
C | Purchase of 1738 Pearl Street | Completed | 749208 | 749208 | 0 | 749208
D | PE Temp. Bldg. Replacement | Completed | 2673247 | 2796548 | 0 | 2797033
E | Remodel Library Village for Math | Completed | 1425565 | 1458204 | 0 | 1458204
F | SM Airport Campus Site Improvements | Completed | 4500000 | 4500000 | 0 | 4060697
G | SM Airport Campus West Building | Completed | 20071124 | 20071124 | 0 | 19561073
H | Theater Arts Renovation | April 2006 | 16992296 | 16992296 | 0 | 11527080
I | Earthquake Rpl. Liberal Arts North | July 2006 | 12473652 | 5352752 | 7120900 | 3598393
J | Music Complex | March 2007 | 4802537 | 4802537 | 0 | 639222
K | Earthquake Rpl. Liberal Arts South | April 2007 | 15891384 | 5266314 | 10625070 | 1023729
L | Shuttle Replacement Parking |  | 17256000 | 17256000 | 0 | 8462
M | North Quad Plaza | October 2007 | 3939759 | 3939759 | 0 | 242160
N | Letters & Sci Demo/Restore | January 2010 | 1192250 | 1192250 | 0 | 0
O | Student Services Building | December 2011 | 40891760 | 23952004 | 16939756 | 707175
P | Science Complex Addition | August 2012 | 14691428 | 0 | 14691428 | 0
Q | Infrastructure & Safety | 2008 | 10000000 | 8400000 | 1600000 | 1375934
R | Restroom Improvements | 2008 | 400000 | 200000 | 200000 | 13955
S | Master Planning | 2008 | 845714 | 845714 | 0 | 625270
T | 14th and Pico Project | On Hold | 14662000 | 319242 | 0 | 319242
| Project Totals |  | 226035147 | 160000000 | 51870996 | 90616777