## Sheet1
| Project Name | Completion | Project Budget | Measure U Allocation | Other Funding | Measure U Expenditures as of 6/30/07
A | Purchase of BAE Airport Site | Completed | 33000000 | 33000000 | 0 | 33000000
B | Emeritus College Facility | Completed | 9603782 | 8909940 | 693842 | 8909940
C | Purchase of 1738 Pearl Street | Completed | 749208 | 749208 | 0 | 749208
D | PE Temp. Bldg. Replacement | Completed | 2797033 | 2797033 | 0 | 2797033
E | Remodel Library Village for Math | Completed | 1458690 | 1458690 | 0 | 1458690
F | SM Airport Campus Site Improvements | Completed | 5000000 | 5000000 | 0 | 4452386
G | SM Airport Campus West Building | Completed | 19694728 | 19694728 | 0 | 19713736
H | Theater Arts Renovation | Completed | 19492296 | 19492296 | 0 | 19457727
I | Earthquake Rpl. Liberal Arts North | Completed | 12473652 | 5352752 | 7120900 | 8134538
J | Music Complex | July 2007 | 3978845 | 1378845 | 2600000 | 998514
K | Earthquake Rpl. Liberal Arts South | July 2007 | 15891384 | 5266314 | 10625070 | 6903981
L | Shuttle Replacement Parking | August 2007 | 18510000 | 18510000 | 0 | 17304431
M | North Quad Plaza | June 2008 | 9000000 | 9000000 | 0 | 800996
N | Letters & Sci Demo/Restore | On Hold | 0 | 0 | 0 | 0
O | Student Services Building | December 2011 | 48858000 | 20803434 | 28054566 | 761106
P | Science Complex Addition | On Hold | 308000 | 308000 | 0 | 184825
Q | Infrastructure & Safety | 2008 | 6859518 | 6859518 | 0 | 2196390
R | Restroom Improvements | 2008 | 100000 | 85000 | 0 | 17501
S | Master Planning | 2008 | 1000000 | 1015000 | 0 | 1013262
T | 14th and Pico Project | On Hold | 319242 | 319242 | 0 | 319242
| Project Totals |  | 209094378 | 160000000 | 49094378 | 129173506