## Sheet1
| Project Name | Completion | Project Budget | Measure U | Other Funding | Measure U Expenditures as of 3/31/05
A | Purchase of BAE Airport Site | Completed | 33000000 | 30000000 | 0 | 0
B | Emeritus College Facility | Completed | 9577223 | 8883381 | 693842 | 8906048
C | Purchase of 1738 Pearl Street | Completed | 749208 | 749208 | 0 | 749208
D | PE Temp. Bldg. Replacement | Completed | 2673247 | 2673247 | 0 | 2680792
E | Remodel Library Village for Math | Completed | 1425565 | 1425565 | 0 | 1418381
F | SM Airport Campus Site Improvements | June 2005 | 6200000 | 6200000 | 0 | 2438504
G | SM Airport Campus West Building | June 2005 | 20071124 | 20071124 | 0 | 12084399
H | Theater Arts Renovation | December 2005 | 16992296 | 16992296 | 0 | 5106568
I | Earthquake Rpl. Liberal Arts North | June 2006 | 12130216 | 5352752 | 6777464 | 693870
J | Music Complex | November 2006 | 4802537 | 4802537 | 0 | 1443120
K | Earthquake Rpl. Liberal Arts South | April 2007 | 13488850 | 2863566 | 10625284 | 845826
L | Shuttle Replacement Parking |  | 17256000 | 17256000 | 0 | 0
M | North Quad Plaza | October 2007 | 3939759 | 3939759 | 0 | 242160
N | Letters & Sci Demo/Restore | January 2010 | 1192250 | 1192250 | 0 | 0
O | Student Services Building | December 2011 | 40891760 | 24067760 | 16824000 | 609252
P | Science Complex Addition | August 2012 | 21215910 | 10613910 | 10602000 | 0
Q | Infrastructure & Safety | 2008 | 5000000 | 5000000 | 0 | 1371109
R | Restroom Improvements | 2008 | 400000 | 400000 | 0 | 3912
S | Master Planning | 2008 | 500000 | 500000 | 0 | 176212
T | 14th and Pico Project | Not Scheduled | 14662000 | 14662000 | 0 | 319242
| Project Totals |  | 226167945 | 177645355 | 45522590 | 39088603