## Sheet1
| Project Name | Completion | Project Budget | Measure S Allocation | Other Funding | Measure S Expenditures as of 6/30/07
1 | Athletic Fields Phase I, Corsair Field | September 2008 | 4010000 | 4010000 | 0 | 259154
1A | Athletic Fields Phase I, John Adams | September 2008 | 2495000 | 2495000 | 0 | 105829
2 | Performing Arts Complex | November 2007 | 38692576 | 35700000 | 2992576 | 30391104
3 | Career Opportunity Center | October 2010 | 32008000 | 32008000 | 0 | 0
4 | Replacement Health, Fitness, PE | July 2011 | 23710434 | 23710434 | 0 | 37525
5 | Early Childhood Development/Childcare | December 2012 | 11318000 | 7000000 | 4318000 | 0
6 | Malibu Site Acquisition and Facility | Not Scheduled | 26000000 | 25000000 | 1000000 | 2698339
7 | Energy Efficiency Projects | In Planning | 25000 | 25000 | 0 | 0
8 | Satellite Campus Parking Facilities and Roadway Improvements | December 2007 | 2600000 | 2600000 | 0 | 0
9 | Underground Parking - Student Services Building | December 2011 | 10951566 | 10951566 | 0 | 0
| Project Totals |  | 151810576 | 143500000 | 8310576 | 33491951